## Cleaning
UNIVERSITY HOSPITAL GALWAY AND MERLIN PARK UNIVERSITY HOSPITAL QUALITY IMPROVEMENT PLAN
HIQA Report of the Unannounced Monitoring Assessment at University Hospital Galway and Merlin Park University Hospital - 21/05/14
Area assessed: Hospital 1, Merlin Park.
Section / Page No. of HIQA Report | Heading and issues highlighted | Action Identified | Owner | Time Frame | Status
3.1 | Cleaning
12 | Dual Role of Catering & Cleaning within the ward each day. Authority recommends that GUH review same with respect to the potential risks associated with this practice and to ensure that cleanliness of the physical environment is effectively managed. | Review options as to how this can be achieved with available resouces | Services Manager | 2014-12-01 | Ongoing

## Environment & Equipment
UNIVERSITY HOSPITAL GALWAY AND MERLIN PARK UNIVERSITY HOSPITAL QUALITY IMPROVEMENT PLAN
HIQA Report of the Unannounced Monitoring Assessment at University Hospital Galway and Merlin Park University Hospital - 21/05/14
Area assessed: Hospital 1, Merlin Park.
Section / Page No. of HIQA Report | Heading and issues highlighted | Action Identified | Owner | Time Frame | Status
3.1 | Environment & Equipment
11 | Heavy dust and grease on bases of beds. | Dust and grease now removed. Results from oil applied during essential maintenance / servicing of electric beds. Will continue to monitor and clean beds. | Cleaning Supervisor | 2014-06-01 | Completed and ongoing monitoring
11 | Dust was observed on pads attached to feet of chairs. | Felt pads to be removed. Review alternative options. | CNM | Jul-Aug-14 | Completed and ongoing review
11 | A black residue was present on shower outlet in pt bathroom (Infusion Unit) | Deep Clean carried out by Cleaning staff. | Cleaning Supervisor | 2014-06-01 | Completed
11 | A rust coloured stain visible on shower curtain in Pt washroom. | Cleaning staff to carry out audit and dispose of rust coloured shower curtain. Shower curtain to be replaced. Audit to be documented. | Cleaning Supervisor | 2014-07-01 | Completed
11 | Staining of floor covering visible in Pt washroom Infusion Bathroom, & Dirty Utility. | Rust stain. Floor covering to be replaced | Maintenance | 2014-08-01 | Scheduled
11 | Rust coloured staining visible on base of 2 IV stands | Both identified and being removed and submit replacement order. | CNM | 2014-08-01 | Scheduled
11 | Clean Utility access to hand hygiene sink restricted by drug trolleys | Maintenance to relocate drug trolleys. | Maintenance | 2014-07-01 | Completed
11 | Wheel areas of drug trolleys were unclean. | Wheel areas cleaned | Clinical Nurse Manager | 2014-07-01 | Completed
11 | Pink stains from chlorhexidine antiseptic which was sitting on the sink. | Maintenance to install holding bracket for antiseptic over sink | Maintenance | 2014-07-01 | Completed
11 | Sticky tape residue on shelving | Cleaned by household staff. | Cleaning Supervisor | 2014-06-01 | Completed
11 | Temporary safety locking mechanisms on a sharps box not engaged. | Contracted company to deliver Waste Mgt training. Training is ongoing to ensure all staff receive same. | Environment & Waste Management Co-ordinator | July- Sept14 | Ongoing
11 | A ceiling tile in Dirty Utility was stained (Single Side of ward) | Replace the tile. | Maintenance | 2014-08-01 | Scheduled
11 | Cardboard boxes stored on floors of linen room & store room opposite. | Linen room and store room reorganised to ensure not repeated in future. | CNM | 2014-06-01 | Completed
12 | Chipped paint observed in patient areas & clean Utility Rm & on ceiling of store Rm opposite Linen Rm was cracked. | Maintenance to carry out remedial painting. | Maintenance | 2014-07-01 | Completed
12 | Chipped paint was observed on radiator, Pt bedside tables and bed frames. | Maintenance to carry out remedial painting and replacement programme. | Buildings & Maintenance Manager | Aug-Dec 2014 | Scheduled
12 | Edges of Pt bedside tables and lockers chipped hindering cleaning. | Replacement programme required. | Buildings & Maintenance Manager | Aug-Dec 2014 | Completion subject to funding approval.

## Hand Hygiene
UNIVERSITY HOSPITAL GALWAY AND MERLIN PARK UNIVERSITY HOSPITAL QUALITY IMPROVEMENT PLAN
HIQA Report of the Unannounced Monitoring Assessment at University Hospital Galway and Merlin Park University Hospital - 21/05/14
Area assessed: Hospital 1, Merlin Park.
Section / Page No. of HIQA Report | Heading and issues highlighted | Action Identified | Owner | Time Frame | Status
3.3 | Hand Hygiene
18 | The design of clinical hand wash sinks in the 3 areas inspected did not conform to the Health Building Note 00-10 Part C: Sanitary assemblies. | Issue is with waste pipes / outlets in sinks. Sinks installed in new developments are compliant. Review of all sinks to be completed. Replacement of non-conforming sinks subject to funding being made available. | Services Manager | Aug-Dec 14 | Ongoing
20 | Hand Hygiene Training records viewed by the Authority for Hospital 1 demonstrated that 73% of staff are up to date with hand hygiene training over a rolling two year period. | 100% of staff in Hospital 1 now trained in Hand Hygiene | Human Resources Dept. Site Manager | 2014-07-01 | Completed
22 | Hospital 1 achieved 80% compliance in a hand hygiene audit completed in January 2014. which is below the pass rate of 90% compliance. Areas which do not attain a minimum of 90% are re-audited within two months. The authority did not view evidence of a re-audit for Hospital 1. | Re-audit carried out in Hospital 1 on 22/05/14. Compliance rate was 86.7% | Infection Prevention & Control Services Manager | 2014-05-01 | Ongoing monitoring
21 | The overall compliance for GUH for 2013 is below the Health Service Executive (HSE's) national target of 90% | GUH now at 92% compliance | Line Managers & All | 2014-07-01 | Ongoing