## Cleaning Equipment
UNIVERSITY HOSPITAL GALWAY AND MERLIN PARK UNIVERSITY HOSPITAL QUALITY IMPROVEMENT PLAN
HIQA Report of the Unannounced Monitoring Assessment at University Hospital Galway and Merlin Park University Hospital - 21/05/14
Area assessed: St. Michael's Ward UHG
Section / Page No. of HIQA Report | Heading and issues highlighted | Action Identified | Owner | Time Frame | Status
3.1 | Cleaning Equipment
11 | Edges and corners of floor in the Cleaners Store Rm were dusty. Authority informed that the room was cleaned at the end of each day but this was not supported by the daily sign-off sheet which had not been signed. | Area cleaned. Toolbox (Training) talk delivered by Contracted Cleaning Company. Evidence of Toolbox Talks attendance can be made available if required. | Site Manager - Contracted Cleaning Company | 2014-06-01 | Completed
11 | Personal clothing stored in cleaners store room. | Personal clothing removed from cleaners store room. Toolbox Talk delivered. Evidence of attendance at Toolbox Talks available if required. | Site Manager - Contracted Cleaning Company | 2014-06-01 | Completed
11 | Plastic debris was present in equipment sink. | Area cleaned. Toolbox Talk delivered. Evidence of attendance at Toolbox Talk available if required. | Site Manager - Contracted Cleaning Company | 2014-06-01 | Completed
11 | No hand hygiene facilities in the cleaning equipment room. | Install sink in cleaners store room. | Buildings & Maintenance Manager | 2014-08-01 | Scheduled

## Comm_Trans Disease Control
UNIVERSITY HOSPITAL GALWAY AND MERLIN PARK UNIVERSITY HOSPITAL QUALITY IMPROVEMENT PLAN
HIQA Report of the Unannounced Monitoring Assessment at University Hospital Galway and Merlin Park University Hospital - 21/05/14
Area assessed: St. Michael's Ward UHG
Section / Page No. of HIQA Report | Heading and issues highlighted | Action Identified | Owner | Time Frame | Status
3.3 Standard 7 | Communicable/Transmissible Disease Control
24 | The authority observed that nebuliser equipment used on St Michaels Ward was for "Single use" but was not disposed of after each user as per hospital policy. | Infection Prevention and Control (IPC) advised all Assistant Directors of Nursing and Ward Managers to re-train staff that nebulisers are for single use, unless patient is on continuous oxygen. Information on the 'single use' symbol is included in Cleaning and Decontamination guidelines and in the Nebuliser policy. IPC to ensure constant re-inforcement of message regarding 'single use' policy. | Director of Nursing / CNM3 Infection Prevention and Control | 2014-07-01 | Completed and ongoing monitoring.
24 | Staff demonstrated an uncertainty regarding the correct procedure around when to dispose of the nebuliser equipment. | Information on single use symbol included in cleaning and decontamination guidelines and in nebuliser policy. Staff educated that nebulisers are for single use. | Clinical Nurse Managers / CNM3 Infection Prevention & Control. | 2014-07-01 | Completed
|  | Stores Manager advised to check with manufacturers to ensure that all equipment for administering nebuliser and oxygen, complies with single use symbol. | Stores Manager | Ongoing | Completed and ongoing
|  | Ward Managers to include above as part of their internal audits. | Clinical Nurse Managers | Ongoing | Ongoing

## Hand Hygiene
UNIVERSITY HOSPITAL GALWAY AND MERLIN PARK UNIVERSITY HOSPITAL QUALITY IMPROVEMENT PLAN
HIQA Report of the Unannounced Monitoring Assessment at University Hospital Galway and Merlin Park University Hospital - 21/05/14
Area assessed: St Michael's Ward UHG
Section / Page No. of HIQA Report | Heading and issues highlighted | Action Identified | Owner | Time Frame | Status
3.3 | Hand Hygiene
3.3.1
18 | The design of clinical hand wash sinks in the 3 areas inspected did not conform to the Health Building Note 00-10 Part C: Sanitary assemblies. | Issue is with waste pipes / outlets in sinks. Sinks installed in new developments are compliant. Review of all sinks to be completed. Replacement of non-conforming sinks subject to funding being made available. | Services Manager | Aug-Dec 14 | Ongoing
18 | Alcohol hand gel dispensers were not available at each point of care, St Michaels Ward. | Facility audit completed by Infection Prevention and Control to identify where gel dispensers were required. Feedback provided to Clinical Nurse Manager and gel dispensers for patient beds ordered and installed. | Buildings & Maintenance Manager | 2014-07-01 | Completed
20 | Hand Hygiene training records viewed by the authority for St Michaels ward showed that 67% of staff have attended hand hygiene training since 1 June 2012. Similar to St Nicholas Ward, the remainder of staff on St Michaels Ward who had not completed training in this period include staff on extended leave and student nurses, therefore the overall percentage of current staff that have been trained is higher than the figures presented. | Training ongoing. 92% of all GUH staff now trained. Hand hygiene training is provided by IP&CS staff at ward level (either with individuals or in group sessions) in order to facilitate staff on the ward. Infection Control nurse has advised nurse managers that Hand Hygiene training records must be held at ward level and updated to ensure all staff have attended as per national guidelines. Ongoing training provided by IP&CS and also by Train the Trainers. Plan in place to display percentage of staff trained in hand hygiene on notice board in each ward. | CNM3 Infection Prevention & Control Services |  | Ongoing
21 | The overall compliance for GUH for 2013 is below the Health Service Executive (HSE's) national target of 90% | The Authority was informed that the hospital plans to carry out four to five hand hygiene audits per month. | CNM3 Infection Prevention & Control Services |  | Ongoing

## Environment & Equipment
UNIVERSITY HOSPITAL GALWAY AND MERLIN PARK UNIVERSITY HOSPITAL QUALITY IMPROVEMENT PLAN
HIQA Report of the Unannounced Monitoring Assessment at University Hospital Galway and Merlin Park University Hospital - 21/05/14
Area assessed: St. Michael's Ward UHG
Section / Page No. of HIQA Report | Heading and issues highlighted | Action Identified | Owner | Time Frame | Status
3.1 | Equipment & Environment
8 | A layer of moderate dust was observed on the floor edges in a patient area in the 7 bedded ward. In addition a used oral hygiene swab and paper wrap were observed on the floor behind the locker. | Area cleaned. Contract cleaning company delivered Toolbox Talk (retraining) to all operatives. | Site Manager - Contracted Cleaning Company | 2014-06-01 | Completed
9 | A light layer of dust was present on electrical fittings located behin the resus trolley. Sticky residue was also noted on the wall. | Area cleaned. Toolbox Talk given. | Site Manager - Contracted Cleaning Company | 2014-06-01 | Completed
9 | Layer of dust on oxygen holder on Resus trolley and the surface of the trolley | Area cleaned. Clinical Nurse Manager to ensure these items are on the daily / weekly cleaning list and maintained in a clean state. | Clinical Nurse Manager(s) | 2014-06-01 | Completed
9 | Oxygen tanks stored behind Resus trolley were dusty & rust coloured staining was observed on the surface of the tanks. Rust coloured staining on Oxygen tanks on main corridor hindering effective cleaning | Oxygen suppliers contacted by Stores Dept and review to take place re replacement of rusted tanks. | Services Manager | July-Sep 2014 | Scheduled
9 | Trolley used for eye care and dressings visibly dirty. | Deep clean carried out. Trolley re-audited in July 2014. Clinical Nurse Manager to review to ensure equipment cleaned on a scheduled basis and maintained in a clean state. | Site Manager - Contracted Cleaning Company and Clinical Nurse Manager. | 2014-06-01 | Completed and ongoing.
9 | Computer keyboard dusty. | Clean carried out. Keyboard cover ordered. Clinical Nurse Manager to review to ensure equipment cleaned on a scheduled basis and maintained in a clean state. | Clinical Nurse Manager - St. Michael's Ward. | 2014-09-01 | Ongoing
9 | Staining present on a Pt bedside table. | Clean carried out. ISS to ensure cleaning of all patient bedside tables. Toolbox talk given. | Site Manager - Contracted Cleaning Company | 2014-06-01 | Completed
9 | The mattress on bed 3 in 7 bedded ward was compromised | Mattress sent for destruction. 3 new mattresses delivered. Mattress audit carried out & will continue on a scheduled basis. | Clinical Nurse Manager - St. Michael's Ward. | 2014-07-01 | Completed and ongoing.
|  | Form for recording 3-monthly mattress audits issued by IP&CS to all nursing managers for dissemination to staff. | Clinical Nurse Manager - St. Michael's Ward. | 2014-06-01 | Completed
|  | One of the findings from IP&CS audits is that mattresses need to be checked as the patient is discharged and three monthly audits carried out. | Clinical Nurse Manager - St. Michael's Ward. | 2014-08-01 | Ongoing
|  | IP&CS recommend that 10 mattresses to be held in stock on site in event of replacements required. | Services Manager | 2014-08-01 | Scheduled
9 | A plastic cover was present on the underside of a shelf on a dressing trolley. | Plastic cover removed and deep clean carried out. Clinical Nurse Manager to review to ensure equipment cleaned on a scheduled basis and maintained in a clean state. | Site Manager - Contracted Cleaning Company and Clinical Nurse Manager. | 2014-06-01 | Completed and ongoing.
9 | Underside of 2 shelves on Pt notes trolley visibly stained | Deep clean carried out. Clinical Nurse Manager to review to ensure equipment cleaned on a scheduled basis and maintained in a clean state. | Site Manager - Contracted Cleaning Company and Clinical Nurse Manager. | 2014-06-01 | Completed and ongoing.
10 | Vinyl covering on a chair in Isolation Rm cracked which could hinder cleaning. | Chair sent for re-covering. Audits of furniture to be carried out on an ongoing basis to ensure maintained in a fit state and suitable for cleaning. | Buildings & Maintenance Manager | 2014-08-01 | Completed and ongoing.
10 | Chipped paint on IV drip stand hindering cleaning | 5 new stands placed on ward. Stands with chipped paint to be disposed of. | Buildings & Maintenance Manager | 2014-07-01 | Completed
10 | PPE used inappropriately during inspection | Observation of practice carried out by Infection Prevention and Control. Re-training also provided by Infection Prevention & Control on an ongoing basis. | Clinical Nurse Manager - St. Michael's Ward. | 2014-06-01 | Completed and ongoing.
10 | Healthcare worker emptying basin of water used for washing a Pt in a designated HH sink. | Address with staff at next ward meeting. Re-training. | Clinical Nurse Manager - St. Michael's Ward. | 2014-06-01 | Completed
10 | Used towels visible on floor - sanitary facilities in 7 Bed and toilets near ENT Rm. | Towels removed. Cleaning operatives re-trained via Toolbox Talk to ensure this area addressed in future. | Site Manager - Contracted Cleaning Company | 2014-06-01 | Completed and ongoing.
10 | Patient consumables were observed in two of the shower rooms inspected.Empty packaging was also present on the window sill of one of the shower rooms. | Laminated signage installed to remind patient to remove consumables after showering. Staff education provided. | Clinical Nurse Manager - St. Michael's Ward. | 2014-07-01 | Completed
10 | Empty packaging present in shower room. | Contracted cleaning company to re-train operatives via Toolbox Talk. | Site Manager - Contracted Cleaning Company | 2014-06-01 | Completed
10 | Paint missing & chipboard was exposed on a wall panel behind a waste bin hindering cleaning. | Ensuite in Room 414 - White Rock needed. | Buildings & Maintenance Manager | 2014-07-01 | Completed
10 | White coloured staining on work surface in clean Utility. | Work surface cleaned. Replacement of work top required. | Buildings & Maintenance Manager | 2014-08-01 | Scheduled
10 | Integrated sharps tray visibly unclean. Sticky tape was present on a drug trolley hindering cleaning. | Deep clean carried out. Clinical Nurse Manager to review to ensure equipment cleaned on a scheduled basis and maintained in a clean state. | Site Manager - Contracted Cleaning Company and Clinical Nurse Manager. | 2014-06-01 | Completed and ongoing.
10 | 3 boxes stacked on floor in Store room hindering cleaning | Ordering of stock to be reviewed and possible re-configuration of store rooms to be examined. | Clinical Nurse Manager - St. Michael's Ward. | 2014-08-01 | Scheduled
10 | Empty Sharps bins stored on floor leading into a toilet not in line with the clutter free objectives of a PWP. | Disposable sharps bins removed and placed in store room. Ordering of stock to be reviewed. | Clinical Nurse Manager - St. Michael's Ward. | 2014-07-01 | Ongoing
10 | Some paper based signage not laminated | (Store room opp Rm 408) Removed by CNM. | Clinical Nurse Manager - St. Michael's Ward. | 2014-06-01 | Completed
10 | Residue was observed on the underside of a commode. | Deep clean carried out. Clinical Nurse Manager to review to ensure equipment cleaned on a scheduled basis and maintained in a clean state. All staff educated to check that commodes are clean prior to use and cleaned after use. | Clinical Nurse Manager - St. Michael's Ward. | 2014-06-01 | Completed and ongoing.
10 | There was no designated hand hygiene sink in Patient Isolation Room | Staff use patient's ensuite and if unable to use that sink they use the hand hygiene sinks on the corridors. Alcohol gel available in patient room. Ongoing review. | Clinical Nurse Manager - St. Michael's Ward and Infection Prevention & Control Services Manager. |  | Ongoing

## Linen
UNIVERSITY HOSPITAL GALWAY AND MERLIN PARK UNIVERSITY HOSPITAL QUALITY IMPROVEMENT PLAN
HIQA Report of the Unannounced Monitoring Assessment at University Hospital Galway and Merlin Park University Hospital - 21/05/14
Area assessed: St. Michael's Ward UHG
Section / Page No. of HIQA Report | Heading and issues highlighted | Action Identified | Owner | Time Frame | Status
3.1 | Linen
10 | Inappropriate items in linen room. Pt Mattress, & continence wear & electrical equipment. | CNM to request doors to enclose part of room for non-linen storage | Buildings & Maintenance Manager | 2014-08-01 | Scheduled
10 | Light dust was present on shelving used for storing clean linen. | Area cleaned. Contracted cleaning company to ensure the shelving is on weekly cleaning schedule. Toolbox Talk given. | Site Manager - Contracted Cleaning Company | 2014-06-01 | Completed and ongoing.

## Waste
UNIVERSITY HOSPITAL GALWAY AND MERLIN PARK UNIVERSITY HOSPITAL QUALITY IMPROVEMENT PLAN
HIQA Report of the Unannounced Monitoring Assessment at University Hospital Galway and Merlin Park University Hospital - 21/05/14
Area assessed: St. Michael's Ward UHG
Section / Page No. of HIQA Report | Heading and issues highlighted | Action Identified | Owner | Time Frame | Status
3.2 | Waste
13 | Door to the waste sub collection area was ajar at the time of inspection. The closing mechanism on the door did not allow it to close completely and there was no handle on the door to assist in closing it. | Repair door. | Buildings & Maintenance Manager | 2014-08-01 | Completed
13 | Paint was missing on the door and door frame of the waste collection room. | Paint door and frame | Buildings & Maintenance Manager | 2014-07-01 | Completed
14 | Temp closing mechanisms on 9 sharps waste disposal observed in Clean Utility were not activated. | Waste Management training to be delivered. Training is ongoing to ensure all staff receive same. | Environmental and Waste Management Co-ordinator | July - Sept-14 | Scheduled
14 | A domestic waste disposal bin was observed to be more than 2/3 full in 7 bed ward, which is not in line with best practice. | Waste Management training to be delivered. Training is ongoing to ensure all staff receive same. | Environmental and Waste Management Co-ordinator | July - Sept-14 | Scheduled
14 | A yellow clinical bag was observed in the general waste bin in the toilet of an isolation room inspected. | Waste Management training to be delivered to ensure reinforcement and implementation of policy, in line with best practice. | Environmental and Waste Management Co-ordinator | 2014-08-01 | Scheduled