## Cleaning Equipment
UNIVERSITY HOSPITAL GALWAY AND MERLIN PARK UNIVERSITY HOSPITAL QUALITY IMPROVEMENT PLAN
HIQA Report of the Unannounced Monitoring Assessment at University Hospital Galway and Merlin Park University Hospital - 21/05/14
Area assessed: St. Nicholas's Ward UHG
Section / Page No. of HIQA Report | Heading and Issues Highlighted | Action Identified | Owner | Time Frame | Status
3.1 | Cleaning Equipment
8 | Floor in the cleaners store was stained and unclean | Daily cleaning schedule and signage to be put in place for Cleaners Store. Toolbox Talk given. | Site Manager - Contracted Cleaning Company | 2014-06-01 | Completed
8 | A ceiling tile above electrical boxes was not in place correctly. | Re-set ceiling tile | Buildings & Maintenance Manager | 2014-08-01 | Completed
8 | Hand towels were stored directly on the floor in a store room which was also used to store cleaning trolleys hindering cleaning | Shelving required opposite Cleaners Store room. | Buildings & Maintenance Manager | 2014-08-01 | Scheduled
8 | While wall-mounted gel dispenser in place at entrance to ward opposite cleaners store, no other hand hygiene facilites at point of care in cleaners store. | Hand hygiene sink to be installed in cleaners store room. | Buildings & Maintenance Manager | 2014-08-01 | Scheduled

## General
UNIVERSITY HOSPITAL GALWAY AND MERLIN PARK UNIVERSITY HOSPITAL QUALITY IMPROVEMENT PLAN
HIQA Report of the Unannounced Monitoring Assessment at University Hospital Galway and Merlin Park University Hospital - 21/05/14
Section / Page No. of HIQA Report | Heading and Issues Highlighted | Action Identified | Owner | Time Frame | Status
N/A | All | Infection Prevention & Control Services issued HIQA Audit Tool to all Ward Managers to be used as a checklist to review practices and ensure compliance with HIQA standards | CNM3 Infection Prevention and Control Services |  | Completed
N/A | All | E-mail sent on 04/06/14 by DoN to all nursing managers to advise staff of responsibilities regarding hygiene. | Director of Nursing |  | Completed
N/A | All | Monthly group hygiene audits by senior managers to be implemented in each area (Director of Nursing; Assitant Directors of Nursing; Infection Prevention & Control Services; Services (FM) Manager, etc. | Director of Nursing | 2014-09-01 | Scheduled

## Hand Hygiene
UNIVERSITY HOSPITAL GALWAY AND MERLIN PARK UNIVERSITY HOSPITAL QUALITY IMPROVEMENT PLAN
HIQA Report of the Unannounced Monitoring Assessment at University Hospital Galway and Merlin Park University Hospital - 21/05/14
Area assessed: St. Nicholas' Ward UHG
Section / Page No. of HIQA Report | Heading and issues highlighted | Action Identified | Owner | Time Frame | Status
3.3 | Hand Hygiene
18 | The design of clinical hand wash sinks in the 3 areas inspected did not conform to the Health Building Note 00-10 Part C: Sanitary assemblies. | Issue is with waste pipes / outlets in sinks. Sinks installed in new developments are compliant. Review of all sinks to be completed. Replacement of non-conforming sinks subject to funding being made available. | Services Manager | Aug-Dec 14 | Ongoing
18 | While alcohol hand gel dispensers were available in clinical areas on St Nicholas' ward, they were not available at the point of care at the end of all patient beds. | Alcohol gel dispensers for patient beds to be ordered. Re-audited in July 2014. | Clinical Nurse Manager - St. Nicholas's Ward | 2014-07-01 | Completed
20 | Hand hygiene training records viewed by the Authority for St Nicholas Ward showed that 65% of staff had carried out training. However, it was explained to the Authority that this percentage included staff who were on extended leave and thus the actual compliance was higher amongst staff available to work. | Training ongoing. 92% of all GUH staff now trained. Hand hygiene training is provided by IP&CS staff at ward level (either with individuals or in group sessions) in order to facilitate staff on the ward. Infection Control nurse has advised nurse managers that Hand Hygiene training records must be held at ward level and updated to ensure all staff have attended as per national guidelines. | Clinical Nurse Manager - St. Nicholas's Ward. | 2014-08-01 | Ongoing
22 | The Authority viewed records of hand hygiene audits which were carried out on St Nicholas' ward between 31 Jan and 17 Feb 2014. A total of 30 hand hygiene observations were viewed in this period and the overall compliance was 83%. The authority was informed that the results of audits, which are emailed to the ward manager, are discussed with staff. | The Authority was informed that the hospital aims to do four and five hand hygiene audits per month. | CNM3 Infection Prevention and Control Services |  | Ongoing

## Env & Eqpt
UNIVERSITY HOSPITAL GALWAY AND MERLIN PARK UNIVERSITY HOSPITAL QUALITY IMPROVEMENT PLAN
HIQA Report of the Unannounced Monitoring Assessment at University Hospital Galway and Merlin Park University Hospital - 21/05/14
Area assessed: St. Nicholas's Ward UHG
Section / Page No. of HIQA Report | Heading and Issues Highlighted | Action Identified | Owner | Time Frame | Status
3.1 | Environment & Equipment
6 | Heavy dust and grease on bases of beds. | Dust and grease now removed. Additional cleaning programme introduced by contracted cleaning company. Supervisors to document cleaning schedule. | Site Manager - Contracted Cleaning Company | 2014-06-01 | Completed and ongoing.
6 | Light dust on top of patients lockers Room 260 | Lockers now cleaned. Cleaning of patient lockers part of standard cleaning schedule and assessed as part of random hygiene audits. | Site Manager - Contracted Cleaning Company | 2014-06-01 | Completed
6 | A mattress cover was stained & a 2nd mattress had pinprick holes visible. | Mattresses sent for destruction and replaced. Mattress audit carried out & will continue on a scheduled basis. | Clinical Nurse Manager - St. Nicholas's Ward | 2014-06-01 | Completed and ongoing.
|  | Form for recording 3-monthly mattress audits issued by IP&CS to all nursing managers for dissemination to staff. | Clinical Nurse Manager - St. Nicholas's Ward | 2014-06-01 | Completed
|  | One of the findings from IP&CS audits is that mattresses need to be checked as the patient is discharged and three monthly audits carried out. | Clinical Nurse Manager - St. Nicholas's Ward | 2014-08-01 | Ongoing
|  | IP&CS recommend that 10 mattresses to be held in stock on site in event of replacements required. | Services Manager | 2014-08-01 | Scheduled
6 | Cracks were observed in the floor covering Room 263. | Replace floor covering | Buildings & Maintenance Manager | 2014-06-01 | Completed
6 | Bed urinals were observed sitting on the floor beside 2 patient beds. | HCA & Nursing staff to ensure bed urinals are emptied in a timely fashion. Staff reminder at next ward meeting. | Clinical Nurse Manager - St. Nicholas's Ward | 2014-06-01 | Completed
6 | Access to patient toilet obstructed in 7 bed Emergency Surgical Unit by patient trolley. | General Manager & Director of Nursing to address with Bed Management re Escalation Plan. | General Manager / Director of Nursing | Aug / Sept 2014 | Scheduled
6 | Black staining was visible around the shower outlet in patient washroom in 7 Bed Emergency Surgical Unit. | On investigation, black staining found to be discolouration resulting from wear and tear. Respraying outlets not an option. Replacement of outlets required. To proceed with tender process for areas identified in hospital. | Buildings & Maintenance Manager | 2014-12-01 | Scheduled
6 | Pink staining was visible on the grouting between shower tiles & bottom of shower curtain. | Grouting cleaned. Toolbox talk given to operatives by contract cleaning company. | Site Manager - Contracted Cleaning Company | 2014-06-01 | Completed
6 | Ceiling tiles in toilet not in place correctly. Rm 260 | Tiles put in place correctly. Ongoing review of fitting / replacement of ceiling tiles. | Buildings & Maintenance Manager | 2014-06-01 | Completed and ongoing.
6 | Sealant around shower outlet in patient washroom damaged hindering effective cleaning (Room 263) | On investigation, damage found to have resulted from wear and tear. Respraying outlets not an option. Replacement of outlets required. To proceed with tender process for areas identified in hospital. | Buildings & Maintenance Manager | 2014-12-01 | Scheduled
6 | Stain on ceiling tile and some tiles not correctly placed | Clean / replace stained tile and place all ceiling tiles in correct positions. Ongoing review of fitting / replacement of ceiling tiles. | Buildings & Maintenance Manager | 2014-07-01 | Completed and ongoing.
6 | Rust coloured staining was visible on the base of 1 IV stand and at the bottom of a 2nd IV stand. Chipped paint was also observed on the base of this IV stand. | IV stands included in cleaning schedule. Replacement IV stands ordered. | Services Support Officer | 2014-08-01 | Scheduled and ongoing
6 | Red staining visible on front & back of Glucometers stored in Pt area. Authority observed stained glucometer in use at Pt bedside. | Glucometers cleaned. Director of Nursing and Infection Prevention & Control issued instructions to all Clinical Nurse Managers regarding ongoing cleaning to reiterate their responsibilities in this regard. Instructions regarding cleaning of Glucometers also included in cleaning and decontamination policy. Audit of wards carried out in June 2014 by IP&C. Glucometer cleaning audits will be carried out routinely by CNM. | Clinical Nurse Manager - St. Nicholas's Ward | 2014-06-01 | Completed and ongoing monitoring
7 | A stained plastic cover in place on the underside of top shelf of dressing trolley and a small amount of plastic on a support bar. | Stained plastic cover removed and trolley cleaned. Clinical Nurse Manager to ensure equipment cleaned on a scheduled basis and maintained in a clean state. | Clinical Nurse Manager - St. Nicholas's Ward | 2014-06-01 | Completed and ongoing.
7 | Wheel areas of dressing trolley unclean and rust coloured staining observed. | Trolley cleaned. Replacement trolley ordered. Clinical Nurse Manager to ensure equipment cleaned on a scheduled basis and maintained in a clean state. | Services Support Officer and Clinical Nurse Manager (St. Nicholas's Ward) | 2014-07-01 | Scheduled and ongoing.
7 | Rust coloured staining on wheel areas of a wheelchair. | Audit of pool of wheelchairs to establish what is required to be replaced. | Portering Manager | 2014-07-01 | Scheduled
7 | Waste disposal bins positioned adjacent to toilet and washroom. | This matter was addressed by staff during the inspection. | Clinical Nurse Manager - St. Nicholas's Ward | 2014-05-01 | Completed
7 | IV stands had rust coloured staining on the base of one and the wheel areas of a 2nd IV stand. Chipped paint was observed on the base of an IV stand. | IV stands included in cleaning schedule. Replacement IV stands ordered. | Services Support Officer | 2014-07-01 | Scheduled and ongoing.
7 | Clean Utility. The floor was stained & unclean with dust & debris. | Cleaned area. Toolbox talk provided to operatives by contract cleaning company. | Site Manager - Contracted Cleaning Company | 2014-06-01 | Completed
7 | Some paper notices not laminated. | Removed on 11.06.14 by CNM. Notification re-issued to all staff to ensure all signs are laminated in future. | Clinical Nurse Manager - St. Nicholas's Ward | 2014-06-01 | Completed
7 | Rust coloured staining visible on wheel areas of drug trolleys | All 3 Drug trolleys need respraying | Buildings & Maintenance Manager | 2014-07-01 | Scheduled
7 | Access to hand wash sink restricted by general waste bin. | Space reconfigured to gain access to hand hygiene sink. | Clinical Nurse Manager - St. Nicholas's Ward | 2014-07-01 | Completed
7 | Sealant behind the sink was stained.Clinic Room. | Replace sealant. | Buildings & Maintenance Manager | 2014-08-01 | Scheduled
7 | Dirty Utility door was unlocked allowing unauthorised access to hazardous cleaning products. | Maintenance to evaluate & cost the new system being trialled in MPUH, Hospital 1, where waist-level fob readers give staff access to the Dirty Utility without the staff needing to touch the door. | Buildings & Maintenance Manager | 2014-08-01 | Completion subject to funding approval.
7 | Dirty Utility Door was unlocked allowing unauthorised access to hazardous cleaning products. (as above) | 'Keep Closed' sign to be placed on door, during interim period. | Clinical Nurse Manager - St. Nicholas's Ward | 2014-08-01 | Scheduled
7 | White residue visible on floor around bed pan washer. Light dust and brown staining observed in places along edge of floor covering adjacent to wall panels | Floor covering to be replaced around bed pan washer | Buildings & Maintenance Manager | 2014-08-01 | Scheduled
7 | Orange Tape on bed pan washer hindering cleaning | Tape placed on machine by Maintenance engineer while await replacement part. Tape to prevent flooding if the button was used. Tape will be removed as soon as replacement part is installed. | Buildings & Maintenance Manager | 2014-08-01 | Scheduled
7 | Some laminated signage curling at edges hindering cleaning | Poster removed on walkabout 11.06.14 by CNM | Clinical Nurse Manager - St. Nicholas's Ward | 2014-07-01 | Completed
7 | Rust coloured staining visible on wheel areas of commodes. The vinyl covering was worn on an armrest on 1 commode & there was sticky tape residue on the legs of another commode. | 3 commodes need wheels replaced. Vinyl covering to be replaced. Clinical Nurse Manager to review condition of commodes on an ongoing basis to ensure fit for purpose and maintained in a clean state. | Buildings & Maintenance Manager and Clnical Nurse Manager (St. Nicholas's Ward). | 2014-07-01 | Scheduled and ongoing.
7 | Cardboard box on floor of store room. | Maintenance to install small storage shelf. | Buildings & Maintenance Manager | 2014-06-01 | Completed
7 | A 2nd store room was cluttered with items Pt crutches, sharps bins hindering cleaning. | Shortage of storage space is an issue. CNM to review ordering of stock. Staff requested not to use floor as storage space and this to be monitored on an ongoing basis by Clinical Nurse Manager. | Clinical Nurse Manager - St. Nicholas's Ward | 2014-06-01 | Completed
7 | Pink staining was observed in a corner of floor under a HH sink on main corridor beside ESU. | Floor cleaned and pink staining removed. | Clinical Nurse Manager - St. Nicholas's Ward | 2014-06-01 | Completed
7 | Rust coloured staining visible under some HH sinks | Contracted Cleaning Company to address with operative. Toolbox talk | Site Manager - Contracted Cleaning Company | 2014-06-01 | Completed
7 | Splash marks visible on walls around wall mounted gels. | Walls cleaned and remedial painting carried out. | Buildings & Maintenance Manager | 2014-06-01 | Completed
7 | Paintwork on walls throughout the ward was scuffed and chipped. | Remedial painting carried out. | Buildings & Maintenance Manager | 2014-06-01 | Completed
8 | Chipped paint observed on Radiators. | Remedial painting carried out. | Buildings & Maintenance Manager | 2014-06-01 | Completed
8 | Chipped paint on patient bedside tables and the edges of the tables were chipped. | Maintenance to arrange programme of replacing table tops and re-spraying of bedside tables. | Buildings & Maintenance Manager | Aug-Dec 2014 | Completion subject to funding approval.

## Isolation Rooms
UNIVERSITY HOSPITAL GALWAY AND MERLIN PARK UNIVERSITY HOSPITAL QUALITY IMPROVEMENT PLAN
HIQA Report of the Unannounced Monitoring Assessment at University Hospital Galway and Merlin Park University Hospital - 21/05/14
Area assessed: St. Nicholas's Ward UHG
Section / Page No. of HIQA Report | Heading and Issues Highlighted | Action Identified | Owner | Time Frame | Status
3.1 | Isolation Rooms
8 | Signage on door of Isolation Room not laminated. | All signage will be laminated in future. ( e.g. 'One visitor per patient' / 'Pt fasting'). | Clinical Nurse Manager - St. Nicholas's Ward | 2014-07-01 | Completed
8 | Staff member observed leaving an Isol. Rm wearing PPE & re-entering wearing same PPE incl gloves which were used to open & close the door. | IP&C delivered training to all staff on the use of PPE and Isolation rooms. | Clinical Nurse Manager - St. Nicholas's Ward | 2014-07-01 | Completed

## Linen
UNIVERSITY HOSPITAL GALWAY AND MERLIN PARK UNIVERSITY HOSPITAL QUALITY IMPROVEMENT PLAN
HIQA Report of the Unannounced Monitoring Assessment at University Hospital Galway and Merlin Park University Hospital - 21/05/14
Area assessed: St. Nicholas's Ward UHG
Section / Page No. of HIQA Report | Heading and Issues Highlighted | Action Identified | Owner | Time Frame | Status
3.1 | Linen
8 | Notice fixed to receptacle with a white linen bag stating "all soiled laundry must be put into alginate bag". Segregation of linen into appropiate colour-coded bags was not in place. | 1. Requisition of Red Laundry Bags from Laundry Dept. 2. Education of staff by Environmental and Waste Management Co-ordinator. | Services Manager | July - Sep 2014 | Ongoing
8 | Linen bag stored on main corridor of ward was observed to be more than 2/3 full. | Retraining of staff to be discussed at next ward meeting. | Clinical Nurse Manager - St. Nicholas's Ward | 2014-06-01 | Completed
8 | Inappropiate items & a trolley were stored in linen store room. | Storage of items to be reviewed. Room no longer used to store linen. Linen presses in use. One additional linen press on order. | Clinical Nurse Manager - St. Nicholas's Ward | 2014-08-01 | Scheduled
8 | Ceiling Tile in linen room was not in place correctly | Re-set ceiling tile | Buildings & Maintenance Manager | 2014-06-01 | Completed
8 | Foot stool in linen store room was unclean | Clean footstool. | Site Manager - Contracted Cleaning Company | 2014-06-01 | Completed
8 | Dust was observed on the floor of the linen room | Area cleaned. Toolbox talk given. | Site Manager - Contracted Cleaning Company | 2014-06-01 | Completed

## Waste
UNIVERSITY HOSPITAL GALWAY AND MERLIN PARK UNIVERSITY HOSPITAL QUALITY IMPROVEMENT PLAN
HIQA Report of the Unannounced Monitoring Assessment at University Hospital Galway and Merlin Park University Hospital - 21/05/14
Area assessed: St. Nicholas's Ward UHG.
Section / Page No. of HIQA Report | Heading and Issues Highlighted | Action Identified | Owner | Time Frame | Status
3.2 | Waste
13 | Temp closing mechanisms on sharps waste disposal in clean utility were not engaged. | Deliver Waste Mgt training. Training is ongoing to ensure all staff receive same. | Environmental and Waste Management Co-ordinator | June - Sept-14 | Scheduled
13 | Brown, wet stain was observed on the floor of the biohazardous waste room. | Spillage due to bin cleaning with water residue leaking after cleaning process. Cleaning programme under review. | Buildings & Maintenance Manager | Ongoing | Ongoing
13 | Cover missing from light | Maintenance to repair | Buildings & Maintenance Manager | 2014-08-01 | Completed
13 | Extraction fan was hanging down from ceiling & not connected to extraction ducting which was visible on adjacent wall. | Maintenance to repair | Buildings & Maintenance Manager | 2014-06-01 | Completed
13 | Ceiling tiles were stained and not in place properly. | Maintenance to reset all misplaced ceiling tiles | Buildings & Maintenance Manager | 2014-07-01 | Completed
13 | Chipped paint was observed on the lids and foot levers of non clinical waste disposal bins. | Replace bin in Waste Store Room. | Services Support Officer | 2014-08-01 | Completed
13 | The lid on the non clinical waste disposal bin in Pt toilet Room 253 not operating properly. | Replace bin. | Services Support Officer | 2014-07-01 | Completed
13 | Rust coloured staining was visible at the base of the clinical waste disposal bin Room 263. | Clinical bin no longer required in this room and was disposed of. | Clinical Nurse Manager - St. Nicholas's Ward | 2014-07-01 | Completed
13 | The lid on the non clinical waste disposal bin in Pt toilet Room 263 was broken. | Replace bin | Services Support Officer | 2014-07-01 | Completed
13 | There was chipped paint on a frame used to hold a sharps waste disposal box in the clean utility. | Carry out audit and replace bins where necessary | Support Services Officer | 2014-07-01 | Completed